## tasks
| Provider | MDPH | DPM | CII
Task 1: Server Build & VPN Access
1. Build ESP server within provider network
Provide patient and encounter count estimates | ü
Provide server specifications |  |  |  | ü
Install OS and configure network | ü
Estimated time:
2. Enable VPN Administrator Access
Provide VPN full-system administrator access to the ESP server | ü
Verify additional needed access | ü
Estimated time:
3. Configure network/firewall to enable reporting to MDPH portal
Configure and verify configuration for network/firewall | ü
Estimated time:
Task 2: Data Extract Creation
1. Map data elements
Complete data specifications table (FileSPec) | ü
Identify how multiple facilities or locations will be identified and managed, as applicable
Reconcile/clarify data elements | ü |  |  | ü
Map reconciled data elements to ESP |  |  |  | ü
Estimated time:
2. Create ASCII files requred for ESP functionality
Develop automated process for daily creation of ASCII caret (^) delimited files for, at minimum, the 5 core files | ü
Establish protocol for naming data files corresponding to ESP specifications (i.e. filename with date appended) | ü
Ensure extract process enables creation of extracts based on custom date ranges if/when needed | ü
Estimated time:
3. Enable data transfer
Implement method of automated file transfer to place core extract files on the ESP server for processing. | ü
Estimated time:
Task 3: ESP Installation & Configuration
1. This task will be handled by CII, however provider IT staff should be available to assist with providing any provider specific configuration information required for set-up. Additionally, provider IT staff should be available to assist with any network or system issues specific to the provider environment. [CII]
Estimated time:
Task 4: Data Extract Validation & Back Data Loading
1. Load and validate test data
Provide test data extracts |  |  |  | ü
Load test data into ESP system | ü
Verify, validate all required data elements are present and correspond to the formatting requirements | ü |  |  | ü
Estimated time:
2. Load and validate historical data
Create historical data extract (minimum of 2 years) | ü
Load historical data extract into ESP system | ü
Verify, validate all required data elements are present and correspond to formatting requirements | ü |  |  | ü
Estimated time:
Task 5: Lab Mapping to Enable Case Detection
For each condition, map associated lab tests within ESP. The number of tests to map varies for each site and condition.
Estimated time:
Task 6: Enable ESP Data Processing & Case Detection Processes
1. Enable all ESP related processes for daily data processing and case detection algorithms. [CII] |  |  |  | ü
2. Collaborate with provider clinical staff to validate from EHR cases created.
Task 7: Implement Reporting
Map local codes to LOINCS/SNOMEDS - labs and non-lab data elements [I added this (remove task 5?)-NC]
Establish connectivity via selected method (e.g. SOAP or Mass Highway) |  |  |  | ü
Configure all required mappings within DPH portal [CII, DPH, Provider]
Confirm cases identified by ESP detection algorithm against site EMR [CII sends list to site]
Compare ESP case list for site against MAVEN [DPH]
HL7 syntax message validation
HL7 message content validation
Switch case reporting to DPH production system [CII, DPH]
Estimated time:
Task 8. Ongoing Support and Maintenance Activities
Data extract changes (additional fields added, etc.)
Support for new lab test mappings
System level support / OS patching
New site/location integration (i.e. new sites added to the feed may require/want back loading of data records, validation, etc.)
Note on B1: :The role of the project manager for each provider would be to ensure that tasks under their purview are assigned, and progress monitored